## Process
PRE-SPR PROCESS
Roles & Responsibilities
Timeframe (time before SPR starts) | Admin | Portfolio coordinator | Team Lead | Team | School
2 months | •Confirms dates of SPR with school | •Put together a SPR team & identifies team lead •If this is a follow up SPR, attempt to ensure continuity (if possible) by including team members from the previous SPR team | •Confirm availability to lead | •Confirm availability for SPR | •Confirm dates of SPR with admin person and staff
1 month | •Sends out self evaluation & SPR tool to school leader If this is a follow up SPR, the following documents must be included: •SIP documentation (completed SIP template and virtuous learning circle) •Previous SPR report |  |  |  | •School leader distributes and workshops the SPR tool with staff •School leader completes the SPR self-evaluation •Informs all relevant stakeholders of the upcoming review (parents, students, staff, board)
3 weeks | •Sends completed SPR self-evaluation to the SPR team |  |  | •Reads through distributed SPR self-evaluation •Team members sends 5 clarifying questions each to team lead on SPR self-evaluation | •School leader sends SPR self-evaluation back to the admin person
1 week | •Compiles SPR orientation pack for review team (see SPR orientation pack) •Ensure there is a calibration video available for the team
SPR
See SPR pack
POST-SPR/PRE-SIP PROCESS
Roles & Responsibilities
Timeframe (time from SPR completion) | Admin | Portfolio coordinator | Team Lead | Team | School
48 hours | • Edits and consolidates quick hits and precise praise to send to school lead, team lead and team |  | •Receives consolidated feedback on quick hits and precise praise | •Receives consolidated feedback | •Receives consolidated feedback
10 days |  |  | •Sends first draft of the final SPR report to the team |  | •To complete evaluation of the SPR experience- team and process: http://bit.ly/1lPjrTa
12 days |  |  | •Consolidates feedback into SPR report | •Sends comments, corrections and feedback on draft SPR report to team lead
14 days |  |  | •Sends final written SPR report to school, team, portfolio coordinator and admin person •Sends SIP template to school lead (excel) |  | •School leader shares and begins to workshop the SIP template with the school
1 month |  | •Engages with team lead and school leader to offer support and clarity on the SIP tool and the process in which to implement it | •Sends support email to school leader: 1. From the report you received what have you and your teachers identified as a priority/priorities. 2. What were some of the reflections from your staff after the review? 3. Have your Staff and board/ SGB seen the report? 4. Have you identified any staff to help with your SIP? •Engages with portfolio coordinator and school leader to offer support and clarity on the SIP tool and the process in which to implement it |  | •Engages with team lead and portfolio coordinator to offer support and clarity on the SIP tool and the process in which to implement it
SIP
Roles & Responsibilities
Timeframe (post SPR) | Admin | Portfolio coordinator | Team Lead | Team | School
1 month |  | •Submits completed SIP document
Interim |  |  | •Supports where needed |  | •School to take the SIP process forward
6 months |  | •Follows up on progress of SIP |  |  | • School to engage with virtuous circle

## Vision, mission & goals
South African Extraordinary Schools Coalition School Improvement Plan
School Name
Vision
Mission
Values

## SIP Template
NOTE: All details in blue are given as an example
Domain 1: Leadership & Management
Sub-domain | Areas of Development (What?) | Baseline (Current) | Target (Goal) | Plan/Activity/Resources (How?) | Planning Timeframe (When?) | Action Timeframe (When?) | Roles and Responsibilities (Who?) | Monitoring and Evaluation (Check)
1.1. Whole School Leadership and Management
1.2. Operational Leadership and Management
1.3. Instructional Leadership and Management | Professional Development (PD) | Little to no PD provided for academic staff | Weekly PD | •Develop annual PD calendar •Assign PD co-ordinator •Consult data and staff to identify areas of PD | •Consult and analyse data to inform staff areas of PD (16 June 2014) •Next staff meeting (18 June 2014) used to consult with staff to identify development areas •Decide on whole staff PD vs targeted PD vs both (23 June 2014) •Formalise and share plan ready by end of following week (23 June 2014) • Discuss formal plan with staff (next staff meeting on 25 June 2014) •Identify and formalise a time for and length of weekly PD | •Implement PD calendar at the beginning of next term (21 July 2014) | •Person 1:Timetable •Person 2:PD co-ordinator •Person 3: Staff PD team Person 4: HoD to do data analysis to inform PD areas •Principal/academic head: Monitoring & Evaluation of the presence and quality of PD sessions | • Monthly M&E of PD by Principal or Academic Head •Examples of questions: Is there a PD co-ordinator and/or team appointed? Is there an annual calendar? Is the PD session occurring once a week? Were needs identified and met?
Potential Challenges |  |  |  |  | Managing Potential Challenges
•Staff resistance and buy-in •Lack of implementation of content covered in PD |  |  |  |  | •Ensure support strategies are in place for staff e.g. regular observations and non-judgemental feedback •Enable HoD to manage the follow up and implementation of development provided in PD
Domain 2: Teaching & Learning
Sub-domain | Area of development (what) | Baseline (Current) | Target (Goal) | Plan/Activity (How?) | Planning Timeframe (When?) | Action Timeframe (When?) | Roles and responsibility (Who?) | Monitoring and Evaluation (Check)
2.1. Teaching Practice | Lack of creative instructional practice | •Absence of creative teaching strategies employed or shared •Students are not fully engaged •Student academic needs not being met •Lack of differentiation | •Adoption of coalition lesson non-negotiables (link to document/webpage) in all classes •Increase student engagement to 100% | • Advocacy of coalition non-negotiables •Establish strategies that increase student engagement and learning (Do-nows, exit tickets etc) and create classroom discussion | •First PD session (21 July 2014) to cover techniques that increase student engagement (Do-nows, exit tickets etc) •All staff to share different strategies proven to increase student engagement in the First PD session •Create template for peer observation and feedback templates (alternatively use coalition templates) •Second PD session (28 July) to cover peer observation (evidence based note taking), non-judgemental feedback and training on the use of the templates | •Teachers to implement techniques covered in PD session (22 July) | • PD co-ordinator to cover coalition non-negotiables •All staff members to implement techniques •Staff members to perform peer observations | •HoDs to compile a schedule of peer observation, supervise its implementation and facilitate feedback •HoD to oversee the observation and feedback process •HoD to check through to evidence-based peer observation that students are engaged 100% e.g. all students writing/whole class discussion etc
2.2. Student interactions
2.3. Lesson plan
2.4. Assessments
Potential Challenges |  |  | Managing Potential Challenges
Aversion to change Staff may still have uncertainty regarding peer observation feedback |  |  | Engage the staff during PD on the impact of increasing student engagement through new techniques PD session to address uncertainties and reflect on the process
Domain 3: Culture & Climate
Sub-domain | Area of development (what) | Baseline (Current) | Target (Goal) | Plan/Activity (How?) | Planning Timeframe (When?) | Action Timeframe (When?) | Roles and responsibility (Who?) | Monitoring and Evaluation (Check)
3.1. Site | Classrooms are bare of displays of student work, subject relevant material | •Environment lacks displays of material to facilitate student learning and development •No evidence of timetables, term plans, lesson plans, assessment plans and data | •Every classroom displays rich materials that enhance learning •Timetables, term plans, lesson plans, assessment plans and data are visible in classrooms | •Dedicate two hours per month for staff and students to work on creating and updating displays for classrooms •Create displays that align with current curriculum content | •Staff meeting used to engage staff on the importance of improving or creating vibrant and relevant displays in classrooms (2 July 2014) •Dates and deadlines for classroom improvement to be set in staff meeting (2 July 2014) | • 50% of walls to be covered with relevant work by the week following the staff meeting (9 July 2014) •90% of walls to be covered by the end of July •Ensure displays are updated (aligned to curriculum) in subsequent dedicated time | •School leader to lead the initial staff meeting to engage in expectations, timelines and additional roles and responsibilities, i.e. the evaluative roles of HoDs •Teachers to work with students on planning, designing and posting classroom displays | •School leader to monitor overall classroom environment •HoD to focus on departmental monitoring of displays in terms of relevance, curriculum alignment etc •HoDs assign new timelines where and if necessary
3.2. Student
3.3. Staff
3.4. Community
Potential Challenges |  |  | Managing Potential Challenges
• Lack of resources • Lack of creativity and ideas |  |  | • Provision of resources. Provide guidance on how to make better use of existing resources. • Make use of student input and provide exemplars
Domain 4: School & Community
Sub-domain | Area of development (What?) | Baseline (Current) | Target (Goal) | Plan/Activity (How?) | Planning Timeframe (When?) | Action Timeframe (When?) | Roles and responsibility (Who?) | Monitoring and Evaluation (Check)
4.1. Stakeholders
4.2. Social development | •The school does not work collaboratively with neighbouring/partner schools in terms of sharing and developing resources, sharing best practice and professional development of teachers | •Lack of regular interaction and communication with neighbouring/partner schools | • Establish regular (monthly) communication with neighbouring/partner schools to discuss possible sharing opportunities • Establish a platform for sharing teaching and learning resources and assessments e.g. dropbox, google docs, etc | •Establish an appropriate date and time for regular communication • Identify relevant contacts in neighbouring/partner schools to ensure regular communication and sharing of resources • Engage on identifying common needs (resources, best practice, etc) • Develop a sharing platform | •School leader to make first contact with neighbouring/partner school leader (18 June) •Each school leader to share contact details of champions in each school who will be involved in the process (end of June) • Champions to set up meeting with HoDs from other schools (by the end of July) •Champions to set up in initial meeting regular subsequent meetings with HoDs to ensure continuity | •Establish sharing platform and communicate the platform to all relevant parties, i.e. school leaders and champions (1 July) •First monthly meeting to start in second week of July • First resources to be shared by end of July | •School leader to make initial communication and identify champion contacts • Identified champion to arrange meeting with other champions • Champion to establish the sharing platform • Champions to share resources | •School leader to follow up with champions, examples of questions to ask are as follows: Has a sharing platform been established? Is there regular contact with neighbouring/partner school champions? Have common needs been identified? Is there adequate sharing of resources by all parties?
Potential Challenges |  |  | Managing Potential Challenges
•Technology limitations •Poor co-ordination •Imbalanced sharing |  |  | • Use multiple sources of technology (skype, phone calls etc) • Replace co-ordinating champion. Provide training and support. • Reinforce and renegotiate commitments.
Note on A2: Samantha De Reuck: Focus area 2 of WSE
Note on A12: Samantha De Reuck: Focus area 4,5 & 6 of WSE
Note on A24: Samantha De Reuck: Focus area 1 & 7 of WSE
Note on A36: Samantha De Reuck: Focus area 3 & 9 of WSE